# Project Proposal: Network Performance Analyzer

CS 5470 – Advanced Computer Networks

Sanskar Thapa • Md Islam • Joshua Soteras

## Project Scope

This project implements a network performance analyzer that systematically evaluates how packet size (MTU) and buffer settings affect network behavior under both TCP and UDP. The core focus is on two well-known networking phenomena: fragmentation and reassembly overhead caused by varying MTU sizes, and bufferbloat.

By running parallel experiments over TCP and UDP, the project produces a comparative analysis of how each protocol responds to these conditions. TCP’s built-in congestion control causes it to adapt dynamically, while UDP transmits without any such mechanism, making the contrast between the two a rich area for measurement and analysis. Key metrics collected include throughput, latency, jitter, and packet loss.

## Implementation Plan

The project will be divided across three team members with the following responsibilities:

- Sanskar Thapa: TCP measurement module: implement a TCP sender/receiver pair that varies packet size and buffer size, collecting throughput and latency data across conditions.

- Md Islam: UDP measurement module: implement a UDP sender/receiver pair under the same conditions, recording metrics including packet loss and jitter which are absent in TCP’s abstraction.

- Joshua Soteras: Data pipeline and visualization: aggregate results from both modules, generate comparative plots (latency vs. packet size, loss vs. buffer size, TCP vs. UDP throughput), and lead the written report and presentation.

All experiments will be run on a controlled local network (or emulated using tools such as tc/netem on Linux) to isolate variables. Both modules will log results to a shared CSV format for unified analysis. The codebase will be written in Python using the socket library, with matplotlib used for visualization.

## Testing & Evaluation Methods

The following experimental variables and metrics will be used to evaluate performance:

- MTU/packet size sweep: test packet sizes from 64 bytes to 64 KB to observe fragmentation effects on latency and loss.

- Buffer size variation: artificially inflate buffer sizes using netem to simulate bufferbloat and measure resulting queuing delay.

- Congestion scenario: introduce competing background traffic to stress-test both protocols and observe congestion response.

- Metrics collected: throughput (Mbps), round-trip latency (ms), jitter (ms variance), and packet loss rate (%).

Results will be validated by running each experiment at least three times and averaging across runs to reduce noise. TCP and UDP results will be plotted side-by-side for each condition to facilitate direct comparison. Final analysis will explain observed differences in terms of protocol-level behavior, supported by the raw data and code submitted with the report.